SIMATS ENGINEERING (SAVEETHA SCHOOL OF ENGINEERING)

Department of Computer Science and Engineering

# CO1 ASSESSMENT TOOL 2  –  Agile Sprint Planning & User Story Workshop

| Course Code: | CSA10 | Course Title: | Software Engineering |
| --- | --- | --- | --- |
| CO Assessed: | CO1 | Assessment: | Assessment Tool 2 – Agile Sprint Planning & User Story Workshop |
| Weightage: | 20% | Total Marks: | 25 |
| CO1 Statement: | Apply advanced methodologies and agile project management techniques to manage software projects effectively |  |  |
| Student Name: | N.Adi Narayana | Reg. No.: | 192525346 |
| Date: |  | Duration: | 60 minutes |

## Code of Conduct

I n.Adi Narayana(192525346)____ (Name / Reg No) certify that this submission is my original work and that I have adhered to the guidelines specified for this assessment. I understand that any violation of academic integrity rules will result in disciplinary action.

Signature of the Student: ____Adi_____________________

## Annexure A – Agile Sprint Planning & User Story Workshop

Instructions to Students:

Each student is assigned an individual software project problem statement. Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

Based on the given problem statement, perform an Agile Sprint Planning and User Story Workshop by applying Agile software engineering practices. Prepare a comprehensive sprint planning document covering the following aspects:

- Identify the Project Vision and Stakeholders o 	Define the project's vision, objectives, and identify all key stakeholders involved.

- Create Epics and User Stories o 	Break down the requirements into Epics and formulate well-structured User Stories using the format: As a <user>, I want <feature>, so that <benefit>.

- Define Acceptance Criteria o 	Write clear and measurable acceptance criteria for each selected user story using the Given–When–Then format or equivalent.

- Prioritize the Product Backlog o 	Organize and prioritize the product backlog based on business value, customer needs, and project dependencies.

- Plan the Sprint Backlog o 	Select high-priority user stories for the first sprint and divide them into actionable development tasks.

- Estimate Effort Using Story Points o 	Assign story points to each selected user story using an appropriate estimation technique (e.g., Fibonacci sequence or Planning Poker) and justify your estimates.

- Present the Sprint Goal and Expected Deliverables o 	Define a clear sprint goal and describe the expected sprint deliverables, including the features to be completed at the end of the sprint.

Introduction

Organizations receive a constant stream of customer support tickets through email, chat, web forms and social media. Each ticket is unstructured text that an agent must read, classify as billing, technical, refund or account access, prioritize and route. When this is done manually it is slow and inconsistent, it does not scale, and critical issues such as outages or payment failures can get buried in the queue. Customers wait longer, agents lose time on sorting, and managers cannot see trends early.

The proposed Customer Support Ticket Classification system integrates Natural Language Processing (NLP), Machine Learning and a ticket routing service into a single platform. The software collects tickets, cleans and masks the text, predicts the category and priority with a confidence score, routes confident predictions to the correct team and sends doubtful ones to a human agent. The agent's correction is stored and used to retrain the model.

Agile Scrum has been selected as the software development methodology because it supports incremental development, continuous stakeholder involvement and rapid adaptation to changing requirements. Machine learning needs experiments, so the team can start with a simple baseline model and improve it sprint by sprint. Each sprint delivers a working software increment, allowing feedback to be included throughout the project.

Project Vision

The vision of the Customer Support Ticket Classification system is to develop a secure, scalable and intelligent software platform that understands every support ticket automatically, so that it reaches the right team with the right priority within seconds. The system aims to reduce response time, remove repetitive sorting work, protect customer data and let support agents focus on solving problems. In the long term, the platform can grow into a multilingual support assistant that also suggests replies and predicts SLA breaches.

Project objectives

- Develop an intelligent platform that classifies tickets by category and priority with a macro-F1 of at least 0.85.

- Route at least 70% of tickets automatically, with a prediction time of about one second.

- Send every low-confidence prediction to a human agent for review.

- Ensure secure access and mask personal data before storage (at least 98% detected).

- Retrain the model regularly using the corrections made by agents.

Stakeholders

- 1.Customers: raise support tickets through email, chat, web forms and social media.

- 2.  Support Agents: resolve tickets and review uncertain predictions.

- 3.  Team Leads and Managers: define categories and priority rules and monitor SLAs.

- 4.  Specialist Departments: Billing, Technical, Account and Refund teams that receive routed tickets.

- 5.  Data Scientists and ML Engineers: prepare data, build, compare and retrain the models.

- 6.  Developers, DevOps and QA: build, test, deploy and monitor the system.

- Product Owner and Business Management: set goals and budget and approve releases.

- Security and Compliance Officer: protect customer data and follow privacy regulations.

Roles and Responsibilities

| Stakeholder | Roles and Responsibilities |
| --- | --- |
| Customers | Raise tickets, describe issues clearly and give feedback; they expect a fast and correct response. |
| Support Agents | Resolve tickets, review low-confidence predictions and correct wrong labels, which become training data. |
| Team Leads / Managers | Define categories and priority rules, monitor SLAs and workload, and plan staffing from dashboards. |
| Specialist Departments | Receive routed tickets and resolve them within agreed time limits. |
| Data Scientists / ML Engineers | Collect and label data, build and compare models, and retrain when performance drops. |
| Developers / DevOps / QA | Build the API and integrations, set up CI/CD, test, deploy and monitor. |
| Product Owner / Management | Set goals and budget, prioritize the backlog, approve releases and measure value. |
| Security and Compliance Officer | Protect customer data, control access and follow privacy regulations. |

The Scrum team consists of the Product Owner, a Scrum Master and a Development Team of four (two developers, one data scientist and one QA engineer). Sprints last two weeks, and Sprint 1 runs from 12 to 23 October 2026.

Create Epics and User Stories

Epic 1 – Ticket Ingestion and Storage

This epic collects tickets from the channels and stores them with their metadata.

US-1: As a support team lead, I want web form and email tickets collected through one interface, so that no ticket is missed.

US-2: As a data scientist, I want tickets stored with subject, body, channel and timestamp, so that I can build training datasets.

Epic 2 – Data Preparation

This epic cleans ticket text, analyses the classes and defines clear label rules.

US-3: As a data scientist, I want ticket text cleaned automatically, so that noise does not reduce accuracy.

US-4: As a data scientist, I want text tokenized, stop words removed and words lemmatized, so that the model sees consistent word forms.

US-5: As a data scientist, I want a class-distribution analysis, so that I can plan how to handle imbalance.

US-6: As a product owner, I want labelling guidelines and a label quality check, so that training data is consistent.

Epic 3 – Security and Privacy

This epic protects customer data before it is stored.

US-7: As a compliance officer, I want personal data masked before storage, so that privacy rules are followed.

Epic 4 – Model Development

This epic builds a baseline classifier and compares advanced models.

US-8: As an ML engineer, I want TF-IDF features with Logistic Regression and SVM baselines, so that we have a performance benchmark.

US-9: As an ML engineer, I want Random Forest, LSTM and BERT compared with the baseline, so that the best model is chosen on evidence.

Epic 5 – Classification, Routing and Review

This epic serves predictions, routes tickets and lets agents review doubtful cases.

US-10: As a helpdesk integrator, I want a REST API returning category, priority and confidence, so that tickets are routed automatically.

US-11: As a support agent, I want a screen to confirm or correct low-confidence tickets in one click, so that corrections become training data.

Epic 6 – Dashboard and Analytics

This epic shows ticket volume and model accuracy to managers.

US-12: As a support manager, I want a dashboard of ticket volume and model accuracy, so that I can plan staffing and SLAs.

Summary of Epics

| Epic | Purpose |
| --- | --- |
| Ticket Ingestion and Storage | Collect and store tickets |
| Data Preparation | Clean data and define labels |
| Security and Privacy | Mask personal data |
| Model Development | Build and compare models |
| Classification, Routing and Review | Predict, route and review tickets |
| Dashboard and Analytics | Monitor volume and accuracy |

Define Acceptance Criteria

Acceptance criteria define the conditions that must be satisfied before a user story is considered complete. The Given–When–Then format gives clear, measurable and testable requirements. They are written here for the seven stories of Sprint 1.

Collect Tickets – Web Form (US-1)

Given a customer fills the web form with subject and body

When the form is submitted

Then the ticket is accepted and a unique ticket ID is returned within 2 seconds.

Collect Tickets – Email (US-1)

Given a customer email reaches the support mailbox

When the connector runs (every 5 minutes)

Then one ticket is created with sender, subject and body, and no duplicate is created.

Store Tickets (US-2)

Given a valid ticket is received

When it is saved

Then subject, body, channel and timestamp are stored with no missing field.

Clean Ticket Text (US-3)

Given a ticket contains HTML tags, URLs and a signature

When the cleaning module runs

Then they are removed and at least 95 of 100 test tickets pass the manual check.

Tokenize and Lemmatize (US-4)

Given the cleaned text "Payments are failing"

When pre-processing runs

Then the output is lowercase, without stop words and lemmatized.

Class-Distribution Analysis (US-5)

Given the labelled historical dataset

When the analysis is run

Then counts and percentages per class are reported and ratios above 3:1 are flagged.

Labelling Guidelines (US-6)

Given 500 tickets labelled independently by two reviewers

When agreement is calculated

Then Cohen's kappa is at least 0.70.

Mask Personal Data (US-7)

Given a ticket contains an email, a phone number and a card number

When masking runs before storage

Then they become [EMAIL], [PHONE] and [CARD], with at least 98% of personal data masked.

Definition of Done: the code is reviewed and merged, all acceptance criteria pass, automated tests are green, no high-severity defects remain, the feature is documented and the Product Owner has accepted it.

Product Backlog Prioritizatin

| Priority | Backlog Item | Business Value | Reason |
| --- | --- | --- | --- |
| High | Store Tickets | High | Foundation for all modules |
| High | Collect Web Form and Email Tickets | High | Brings real data into the system |
| High | Mask Personal Data | High | Privacy and compliance |
| High | Clean Ticket Text | High | First step of the NLP pipeline |
| High | Tokenize and Lemmatize | High | Completes pre-processing |
| High | Labelling Guidelines | High | Consistent training labels |
| High | Class-Distribution Analysis | High | Guides imbalance handling |
| High | Baseline Model | High | Early benchmark and value |
| High | REST API and Review Screen | High | Enables automatic routing |
| Medium | Compare Advanced Models | Medium | Improves accuracy |
| Medium | Manager Dashboard | Medium | Administrative analysis |
| Low | Multilingual Tickets | Low | Future enhancement |
| Low | Suggested Replies | Low | Future enhancement |
| Low | SLA-Breach Prediction | Low | Future enhancement |

## Product Backlog Prioritization Justification

High-priority items are implemented first because they are essential for delivering a working first release. Storage, privacy and data quality come first because every later step depends on them, and a simple baseline model comes before the costly LSTM and BERT work. Medium-priority items improve accuracy and management after the core modules are completed. Low-priority features are enhancements that can be scheduled in later sprints without affecting the primary objectives.

Sprint Bavklog

Sprint 1 takes US-1 to US-7 (26 story points). Team capacity is 4 members × 8 usable days × 6 focused hours = 192 hours, and the planned tasks total 136 hours (71%).

| Story | Tasks | Hours |
| --- | --- | --- |
| US-1 | Design schema and API; build endpoint; build email connector; connect web form; write tests | 34 |
| US-2 | Design tables; create migration scripts; test queries and indexes | 11 |
| US-3 | Define cleaning rules; code HTML, URL and signature removal; test 100 noisy tickets; review | 15 |
| US-4 | Tokenization and stop words; lemmatization; build pipeline module; batch test | 11 |
| US-5 | Count classes; create charts and imbalance ratio; write report; review with Product Owner | 10 |
| US-6 | Draft definitions; workshop with leads; label 500 tickets and compute kappa; finalize guideline | 18 |
| US-7 | List personal data patterns; code masking rules; test false positives; security review | 19 |
| Enabler | Set up repository and CI pipeline; integration test and demo preparation | 18 |
| Total |  | 136 |

## Sprint Backlog Justification

Sprint 1 builds the data foundation of the project: ticket collection, storage, privacy masking, text preparation and labelling rules. These stories are small enough to finish in one sprint, they are needed by every later story, and they let stakeholders see a working intake and a clear class report. About 29% of capacity is kept free as a buffer because this is the first sprint and no velocity is known yet.

10.Story point Estimation

Story Point Estimation is an Agile technique used to estimate the relative effort, complexity and uncertainty of each user story. Instead of estimating time directly, the team estimates size using Planning Poker with the Fibonacci sequence (1, 2, 3, 5, 8, 13), because larger work carries more uncertainty. US-2 (a simple database table) was the 3-point reference story.

| User Story | Story Points | Justification |
| --- | --- | --- |
| US-1 Collect Tickets | 8 | Two channels, validation, duplicates, email connector |
| US-2 Store Tickets | 3 | Simple table design, reference story |
| US-3 Clean Text | 3 | Rule-based cleaning of noisy text |
| US-4 Tokenize, Lemmatize | 2 | Ready libraries such as NLTK or spaCy |
| US-5 Class Analysis | 2 | Analysis and charts on existing data |
| US-6 Labelling Guidelines | 3 | Workshop and sample labelling |
| US-7 Mask Personal Data | 5 | Careful patterns and privacy testing |
| US-8 Baseline Model | 8 | Features, training and evaluation |
| US-9 Compare Models | 13 | LSTM and BERT need heavy computing |
| US-10 REST API | 8 | Confidence score and integration |
| US-11 Review Screen | 8 | New user interface and feedback storage |
| US-12 Dashboard | 8 | Charts and live data |

## Justification

The Fibonacci sequence is widely used in Agile because larger tasks have more uncertainty than smaller ones. The Sprint 1 stories (US-1 to US-7) total 26 points, about 5.2 hours per point, and the largest of them (8 points) fits within one sprint. Story points help the team estimate consistently and plan sprints without exact hour-based estimates.

11.Sprint Goal

The objective of Sprint 1 is to deliver a working data foundation for the Customer Support Ticket Classification system. By the end of the sprint, the team will have a pipeline that collects tickets from the web form and email, masks personal data, stores the tickets and prepares clean text, together with a labelling guideline and a class-distribution report. Completing these features lets stakeholders evaluate a working intake and allows baseline model training to begin in Sprint 2.

12.Expected Sprint Deliverables

| Deliverable | Description |
| --- | --- |
| Ticket Intake Module | Collect web form and email tickets |
| Database | Store tickets and metadata |
| Privacy Masking Module | Replace personal data with tokens before storage |
| Pre-processing Pipeline | Clean, tokenize, remove stop words and lemmatize text |
| Class-Distribution Report | Counts, imbalance ratio and recommendations |
| Labelling Guideline | Definitions, examples and agreed labels |
| CI Pipeline | Automatic build and test on every commit |
| Testing Report | Document testing activities and results |

13.Sprint Review

At the end of Sprint 1, on 23 October 2026, the Scrum Team demonstrates the completed software increment to the stakeholders. The implemented features are reviewed against the acceptance criteria, and stakeholders provide feedback regarding usability, functionality and possible enhancements. Any newly identified requirements are added to the product backlog for future sprints.

14.Sprint Retrospective

After the Sprint Review, the development team conducts a Sprint Retrospective to evaluate the sprint process. The team discusses what went well, identifies challenges such as email connector issues, label disagreements or testing delays, and proposes improvements including a better task breakdown, more automated testing and clearer communication. These improvements are applied in the next sprint to increase productivity and software quality

15.Agile Workflow

The flow below summarizes the complete Agile process followed in this report, from the vision to the next sprint. After the retrospective, the cycle starts again with the next sprint planning.

| 1. Project Vision | → | 2. Stakeholder Identification | → | 3. Requirement Gathering | → | 4. Product Backlog |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | ↓ |
| 8. Sprint Planning | ← | 7. Acceptance Criteria | ← | 6. User Stories | ← | 5. Epics |
| ↓ |  |  |  |  |  |  |
| 9. Story Point Estimation | → | 10. Sprint Backlog | → | 11. Development | → | 12. Testing |
|  |  |  |  |  |  | ↓ |
|  |  | 15. Next Sprint | ← | 14. Sprint Retrospective | ← | 13. Sprint Review |

16.Conclusion

The Customer Support Ticket Classification system demonstrates the effective application of Agile Scrum principles in software development. By dividing the project into epics, user stories, product backlog items and sprint backlogs, the team can develop the system incrementally while continuously using stakeholder feedback. Story point estimation supports realistic planning, acceptance criteria ensure quality, and sprint reviews and retrospectives encourage continuous improvement. Overall, Agile Scrum enables the development of a secure, scalable and user-focused solution that classifies and routes customer support tickets quickly and accurately.

### Rubrics for Calculation

| Criteria | Excellent (5 Marks) | Good (3 Marks) | Satisfactory (2 Marks) | Needs Improvement (1 Mark) |
| --- | --- | --- | --- | --- |
| Project Vision & Stakeholder Identification | Project vision is clear, comprehensive, and aligned with the problem statement. All relevant stakeholders and their roles are correctly identified. | Vision is clear with minor omissions. Most stakeholders are correctly identified. | Vision is partially defined. Some stakeholders are missing or incorrectly identified. | Vision is unclear or incomplete. Stakeholders are poorly identified or missing. |
| Epics & User Stories | Epics are well-defined and user stories are complete, follow Agile format, and fully capture functional requirements. | Epics and user stories are mostly complete with minor formatting or requirement issues. | User stories are partially complete with limited Agile structure. | User stories are incomplete, unclear, or do not follow Agile practices. |
| Acceptance Criteria | Acceptance criteria are specific, measurable, testable, and aligned with all user stories. | Acceptance criteria are mostly clear and testable with minor gaps. | Acceptance criteria are partially defined and lack clarity or completeness. | Acceptance criteria are missing or not aligned with user stories. |
| Product Backlog Prioritization & Sprint Planning | Product backlog is logically prioritized, sprint backlog is realistic, and task breakdown is complete. | Backlog prioritization and sprint planning are mostly appropriate with minor issues. | Prioritization or sprint planning is partially complete with limited justification. | Backlog prioritization and sprint planning are poorly organized or incomplete. |
| Story Point Estimation, Sprint Goal & Presentation | Story point estimation is well justified, sprint goal is clear, deliverables are realistic, and presentation is professional and well organized. | Estimation and sprint goal are mostly appropriate with minor inconsistencies. Presentation is clear. | Estimation or sprint goal lacks justification. Presentation is adequate but incomplete. | Estimation is unrealistic or missing. Sprint goal, deliverables, and presentation are unclear or incomplete. |

| Criteria | Mark |
| --- | --- |
| Project Vision & Stakeholder Identification | /5 |
| Epics & User Stories | /5 |
| Acceptance Criteria | /5 |
| Product Backlog Prioritization & Sprint Planning | /5 |
| Story Point Estimation, Sprint Goal & Presentation | /5 |
| TOTAL | /25 |